PROJECT WORKPLAN & BUSINESS REQUIREMENTS DOCUMENT

Cryptographic Algorithm Migration: DES / 3DES → AES

SDLC-Aligned Migration Template — Configurable for Any Legacy-to-Modern Cryptographic Transition

Prepared for: [Organization Name]

System(s) in Scope: [System / Application / Environment Name]

Document Owner: [Project Sponsor / Security Lead]

Version: [0.1 – Draft]

Date: [Insert Date]

Classification: [Internal / Confidential]

# Table of Contents

# 1. Document Control

## 1.1 Revision History

| Version | Date | Author | Description of Change |
| --- | --- | --- | --- |
| 0.1 | [Date] | [Name] | Initial draft from discovery discussion |
| 1.0 | [Date] | [Name] | Baseline approved for kickoff |

## 1.2 Approvals

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Executive Sponsor | [Name] |  | [Date] |
| CISO / Security Lead | [Name] |  | [Date] |
| Project Manager | [Name] |  | [Date] |
| Compliance / Audit Lead | [Name] |  | [Date] |

## 1.3 Distribution List

[Insert names/roles of individuals or groups who receive this document — e.g., IT Security, Infrastructure, Application Owners, Legal/Compliance, Internal Audit, Vendor Management.]

# 2. Executive Summary

This document defines the business requirements and full Software/System Development Life Cycle (SDLC) workplan for migrating cryptographic implementations from the Data Encryption Standard (DES) and Triple DES (3DES/TDEA) to the Advanced Encryption Standard (AES). It is built as a reusable template: every bracketed field is a variable to be populated for the specific organization and system(s) undergoing migration, so the same document set can be reused across future legacy-to-modern cryptographic transitions (e.g., SHA-1 → SHA-2/3, RSA-2048 → post-quantum algorithms).

The driver for this migration is both a security and a compliance imperative. NIST formally disallowed 3-key TDEA (3DES) for applying cryptographic protection to federal information after December 31, 2023 under NIST Special Publication (SP) 800-131A Revision 2, and a Revision 3 draft (released for comment in late 2024) signals a further industry-wide move toward a 128-bit minimum security strength by December 31, 2030. Organizations still relying on DES or 3DES anywhere in their environment carry both an active security exposure and a growing compliance/audit finding risk.

This document is organized in two parts: (1) a Business Requirements Document (BRD) defining what must be true when the project is complete, and (2) a phase-by-phase SDLC Project Workplan defining how the organization gets there, including a Work Breakdown Structure, RACI matrix, risk register, and a key management sub-plan.

# 3. Business Requirements Document (BRD)

## 3.1 Business Objectives

- Eliminate use of DES and 3DES/TDEA for encryption of data at rest and in transit across all in-scope systems, applications, and infrastructure.

- Establish AES (128-bit minimum; 256-bit for high-sensitivity data classes) as the organizational standard symmetric cipher, consistent with FIPS 197 and NIST SP 800-131A Rev. 2.

- Maintain continuous data availability and integrity throughout the transition, with no unplanned downtime to production services.

- Achieve and evidence compliance with applicable regulatory frameworks (e.g., PCI DSS, HIPAA, GLBA, FedRAMP/FISMA) by project close.

- Modernize key management practices (generation, distribution, rotation, storage, destruction) in line with current NIST guidance.

- Produce a reusable migration playbook and set of artifacts that can be applied to future cryptographic transitions.

## 3.2 Scope

### In Scope

- All applications, databases, middleware, and interfaces identified in the cryptographic inventory (Section 4.2) as using DES or 3DES.

- Hardware Security Modules (HSMs), key management systems (KMS), and certificate/key stores supporting in-scope systems.

- VPN gateways, network appliances, and legacy protocol endpoints (e.g., older TLS cipher suites) using DES/3DES.

- Third-party and vendor-managed systems where the organization has contractual leverage to require remediation.

- [Insert organization-specific systems: e.g., mainframe batch encryption, payment switch, archival/backup encryption]

### Out of Scope

- Asymmetric algorithm migration (e.g., RSA, ECC) and post-quantum cryptography readiness — tracked as a separate initiative unless explicitly added.

- Hashing algorithm migration (e.g., SHA-1 deprecation) — tracked as a separate initiative unless explicitly added.

- [Insert any systems explicitly excluded, with rationale — e.g., systems already scheduled for decommission.]

## 3.3 Stakeholders

| Stakeholder | Interest / Role |
| --- | --- |
| Executive Sponsor | Funds and champions the project; accepts residual risk |
| CISO / InfoSec | Owns cryptographic standards, approves target-state architecture |
| Enterprise/Solution Architect | Validates technical approach and system compatibility |
| Application Owners | Own in-scope systems; approve change windows and testing |
| Infrastructure / Network Team | Executes changes to HSMs, VPNs, network devices |
| Database Administrators | Execute data re-encryption / transparent data encryption changes |
| Compliance / Internal Audit | Confirms regulatory alignment and evidences controls |
| Legal / Vendor Management | Manages third-party contractual remediation requirements |
| Project Management Office | Tracks schedule, budget, risk, and reporting |
| End Users / Help Desk | Informed of any user-facing impact (e.g., re-authentication) |

## 3.4 Functional Requirements

| ID | Requirement | Priority |
| --- | --- | --- |
| FR-01 | System shall support AES encryption (minimum AES-128, target AES-256) for all newly encrypted data. | Must |
| FR-02 | System shall provide a mechanism to re-encrypt or migrate existing DES/3DES-protected data to AES without data loss. | Must |
| FR-03 | System shall support a dual-algorithm transition mode (decrypt legacy, encrypt new) where instant cutover is not feasible. | Should |
| FR-04 | Key management system shall generate, distribute, rotate, and destroy AES keys per organizational key management policy. | Must |
| FR-05 | System shall log all cryptographic configuration changes for audit purposes. | Must |
| FR-06 | System shall provide rollback capability to a known-good state during the transition window. | Should |
| FR-07 | [Insert additional organization/system-specific functional requirement.] | [Priority] |

## 3.5 Non-Functional Requirements

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-01 | Performance | AES implementation shall not increase transaction latency beyond [X]% of current baseline; leverage AES-NI/hardware acceleration where available. |
| NFR-02 | Availability | Migration activities shall not cause unplanned downtime; planned maintenance windows require [X] days' advance notice. |
| NFR-03 | Security | Key sizes, modes of operation, and padding schemes shall conform to NIST SP 800-38 series guidance (e.g., avoid ECB mode). |
| NFR-04 | Auditability | All migration activity shall be traceable to a change ticket, approver, and rollback plan. |
| NFR-05 | Scalability | Solution shall accommodate future onboarding of additional systems without re-architecture. |

## 3.6 Regulatory & Compliance Requirements

The following table maps the migration to the primary external standards and regulatory frameworks. See Appendix A for full references. Confirm with Compliance/Legal which frameworks are mandatory for the specific organization and data types in scope.

| Framework | Relevance to This Migration |
| --- | --- |
| NIST SP 800-131A Rev. 2 | Authoritative transition guidance; disallows 3-key TDEA encryption after Dec 31, 2023 for federal/regulated use; defines deprecated vs. disallowed algorithm states. |
| FIPS 197 (AES) | Defines the AES algorithm specification (128/192/256-bit keys) that is the migration target. |
| FIPS 140-3 | Governs validated cryptographic modules; any HSM/KMS handling regulated data should use a FIPS 140-3 validated module. |
| PCI DSS v4.0 | Prohibits use of DES/3DES for protecting cardholder data; requires documented cryptographic key management and periodic review of crypto-suites. |
| HIPAA Security Rule | Requires 'addressable' encryption safeguards for ePHI; weak/deprecated ciphers are an increasingly indefensible position in a risk analysis. |
| NIST Cybersecurity Framework (CSF) 2.0 | Provides the PROTECT (Data Security) function context for embedding this migration into broader risk management. |
| ISO/IEC 27001 / 27002 | Annex A cryptographic controls (A.8.24 in 2022 revision) expect a documented cryptography policy and key lifecycle management. |
| [Sector-specific: SOX, GLBA, FedRAMP, state privacy law] | [Insert if applicable to the organization.] |

## 3.7 Assumptions, Constraints & Dependencies

### Assumptions

- A complete inventory of cryptographic assets does not yet exist and will be produced during Phase 2 (Discovery).

- Budget and staffing for a potential hardware refresh (for devices lacking AES support) will be approved as a contingency, not assumed up front.

- Business units will make systems and staff available for the testing windows defined in the schedule.

### Constraints

- [Insert fixed compliance deadline, e.g., next PCI assessment date, audit cycle, or contractual date.]

- [Insert budget ceiling, freeze windows (e.g., no changes during peak retail season), or resourcing constraints.]

### Dependencies

- Availability of a FIPS 140-3 validated HSM/KMS platform supporting AES key sizes.

- Vendor cooperation for any third-party or SaaS systems requiring remediation.

- Completion of the cryptographic inventory before detailed design work can begin.

# 4. SDLC Project Workplan

The workplan follows a standard seven-phase SDLC, adapted for a cryptographic migration. Each phase lists its objective, key activities, deliverables, and entry/exit criteria so the phase gate can be formally reviewed and signed off before proceeding — consistent with a change-controlled, auditable migration.

## 4.1 Phase 1 — Initiation

Objective: Formally charter the migration project, secure sponsorship, and establish governance.

### Key Activities

- Draft and approve project charter, including business case referencing SP 800-131A Rev. 2 timelines.

- Identify executive sponsor, project manager, and core project team.

- Define high-level scope, budget envelope, and target completion date.

- Establish project governance structure and steering committee cadence.

### Deliverables

- Approved Project Charter

- RACI matrix (draft) — see Section 5

- Initial stakeholder register

| Entry Criteria | Exit Criteria |
| --- | --- |
| Business need documented; executive sponsor identified. | Charter signed; project team resourced; kickoff scheduled. |

Primary Roles Engaged: Executive Sponsor, PMO, CISO

## 4.2 Phase 2 — Planning & Discovery (Cryptographic Inventory)

Objective: Identify every system, application, protocol, and device using DES/3DES, and assess compatibility with AES.

### Key Activities

- Conduct full cryptographic asset inventory across applications, databases, HSMs, embedded/IoT devices, VPNs, and third-party systems.

- Classify each finding by data sensitivity, business criticality, and regulatory applicability.

- Assess AES compatibility: software-only update vs. firmware update vs. hardware replacement.

- Confirm HSM/KMS support for AES key sizes and required modes of operation.

- Develop the detailed Work Breakdown Structure, resource plan, and schedule (Section 5).

- Complete initial Risk Register (Section 7).

### Deliverables

- Cryptographic Inventory Report

- Compatibility & Gap Assessment

- Detailed Work Breakdown Structure and schedule

- Baseline Risk Register

| Entry Criteria | Exit Criteria |
| --- | --- |
| Charter approved; project team resourced. | Inventory validated by system/application owners; gap assessment reviewed by architecture and security. |

Primary Roles Engaged: Security Architecture, Application Owners, Infrastructure

## 4.3 Phase 3 — Analysis & Design

Objective: Translate the BRD and inventory findings into a target-state cryptographic architecture and migration approach per system.

### Key Activities

- Define target AES key lengths and approved modes of operation (e.g., GCM, CBC with proper padding) per NIST SP 800-38 series.

- Design the Key Management Plan: generation, distribution, storage, rotation, and destruction (see Section 8).

- Design the dual-support / transition approach for systems that cannot cut over instantly (legacy decrypt, new encrypt).

- Design data re-encryption approach for data at rest (batch re-encryption vs. re-encrypt-on-access).

- Produce per-system migration runbooks, including rollback procedures.

- Conduct design review and threat model with Security Architecture.

### Deliverables

- Target-State Cryptographic Architecture document

- Key Management Plan

- Per-system Migration Runbooks

- Design Review sign-off

| Entry Criteria | Exit Criteria |
| --- | --- |
| Inventory and gap assessment complete and approved. | Architecture and runbooks approved by CISO/Security Architecture; rollback plans defined for every in-scope system. |

Primary Roles Engaged: Security Architecture, Enterprise Architecture, DBAs, Network Engineering

## 4.4 Phase 4 — Development / Implementation

Objective: Implement AES support in code, configuration, and infrastructure per the approved design, in non-production environments first.

### Key Activities

- Update application code/libraries to use AES (favor vetted cryptographic libraries; avoid custom cryptographic implementations).

- Apply firmware/software updates or provision replacement hardware for devices lacking native AES support.

- Configure HSM/KMS to generate and manage AES keys per the Key Management Plan.

- Implement dual-algorithm transition logic where required.

- Update CI/CD pipelines, configuration management, and infrastructure-as-code artifacts to enforce AES as the standard.

- Peer review and static/security code review of all cryptography-related changes.

### Deliverables

- Updated application/system builds in a lower (dev/test) environment

- Updated infrastructure configuration

- Code/security review records

| Entry Criteria | Exit Criteria |
| --- | --- |
| Design and Key Management Plan approved. | Build deployed successfully to test environment; code review complete with no open critical findings. |

Primary Roles Engaged: Development, Infrastructure, Security Engineering

## 4.5 Phase 5 — Testing & Validation

Objective: Validate that AES implementation is functionally correct, secure, and does not degrade performance, before production rollout.

### Key Activities

- Functional testing: encryption/decryption correctness, data integrity checks, error handling.

- Interoperability testing across all systems that exchange encrypted data with the migrated system.

- Transition-state testing: confirm dual-algorithm mode correctly decrypts legacy data while encrypting new data as AES.

- Performance/load testing against the NFR-01 latency threshold, with and without hardware AES acceleration.

- Security testing: verify no fallback to DES/3DES is possible; validate key handling and absence of hard-coded keys.

- Backup and disaster-recovery testing under the new encryption scheme.

- User Acceptance Testing (UAT) sign-off from application owners.

### Deliverables

- Test Plan and Test Case Results

- Performance Test Report

- Security Test / Validation Report

- UAT Sign-off

| Entry Criteria | Exit Criteria |
| --- | --- |
| Build available in test environment; test plan approved. | All test cases pass or have documented/accepted exceptions; UAT sign-off obtained; no critical/high security findings open. |

Primary Roles Engaged: QA, Security Testing, Application Owners, Performance Engineering

## 4.6 Phase 6 — Deployment / Phased Rollout

Objective: Deploy the validated AES implementation to production using a risk-based, phased approach rather than a single big-bang cutover.

### Key Activities

- Sequence rollout waves from lowest to highest business criticality, per the phased rollout strategy.

- Execute approved change management process for each wave, including scheduled maintenance windows.

- Monitor each wave post-deployment for functional or performance regressions before proceeding to the next wave.

- Execute data re-encryption for at-rest data per the design (batch or on-access), tracking completion percentage.

- Maintain rollback readiness for each wave per the runbooks.

- Communicate changes to affected internal teams and, where relevant, external partners/customers.

### Deliverables

- Production deployment records per wave

- Data re-encryption completion tracking

- Post-deployment monitoring reports

- Updated Risk Register reflecting closed migration risks

| Entry Criteria | Exit Criteria |
| --- | --- |
| Testing phase exit criteria met; change approvals obtained. | All planned waves deployed; no unresolved Sev-1/Sev-2 incidents attributable to the migration; legacy algorithm usage confirmed disabled per wave. |

Primary Roles Engaged: Change Management, Infrastructure, Application Owners, Help Desk

## 4.7 Phase 7 — Post-Implementation, Maintenance & Closeout

Objective: Confirm legacy algorithms are fully retired, formalize the new steady-state, and close the project with lessons learned.

### Key Activities

- Conduct a final cryptographic scan to confirm no DES/3DES usage remains anywhere in scope.

- Decommission or securely destroy legacy keys per the Key Management Plan's destruction procedures.

- Update security policy, standards, and architecture documentation to reflect AES as the enforced standard.

- Compile compliance evidence package for auditors (PCI DSS, HIPAA, etc. as applicable).

- Conduct project retrospective / lessons-learned session.

- Transition ongoing key rotation and monitoring to standard operations (BAU) teams.

- Archive this document set as the reusable template for the next cryptographic migration.

### Deliverables

- Final Validation / Attestation Report (legacy algorithm retirement confirmed)

- Compliance Evidence Package

- Lessons Learned Report

- Updated organizational cryptography standard

- Reusable Migration Template (this document, genericized)

| Entry Criteria | Exit Criteria |
| --- | --- |
| All rollout waves complete; monitoring shows stable steady state. | Sponsor formally accepts project closure; legacy algorithms confirmed disabled/removed; documentation archived. |

Primary Roles Engaged: PMO, CISO, Compliance/Audit, Operations

# 5. Work Breakdown Structure (WBS) — Template

Populate durations, owners, and dates for the specific engagement. Dependencies reference the Task ID column.

| ID | Task | Phase | Owner | Duration | Depends On |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Charter approval & kickoff | Initiation | PM | [X] wks | — |
| 2.1 | Cryptographic asset inventory | Discovery | Security Architecture | [X] wks | 1.1 |
| 2.2 | Compatibility & gap assessment | Discovery | Infrastructure | [X] wks | 2.1 |
| 2.3 | Detailed schedule & risk register | Discovery | PM | [X] wks | 2.2 |
| 3.1 | Target architecture & key mgmt plan | Design | Security Architecture | [X] wks | 2.3 |
| 3.2 | Per-system migration runbooks | Design | App Owners / Architecture | [X] wks | 3.1 |
| 4.1 | Application/library updates (dev) | Build | Development | [X] wks | 3.2 |
| 4.2 | HSM/KMS AES configuration | Build | Infrastructure | [X] wks | 3.1 |
| 5.1 | Functional & interoperability testing | Test | QA | [X] wks | 4.1, 4.2 |
| 5.2 | Performance & security testing | Test | Security Testing | [X] wks | 5.1 |
| 5.3 | UAT sign-off | Test | App Owners | [X] wks | 5.2 |
| 6.1 | Wave 1 production rollout (low criticality) | Deploy | Change Mgmt | [X] wks | 5.3 |
| 6.2 | Wave 2–N production rollout | Deploy | Change Mgmt | [X] wks | 6.1 |
| 6.3 | At-rest data re-encryption | Deploy | DBAs | [X] wks | 6.2 |
| 7.1 | Final scan & legacy key destruction | Closeout | Security Architecture | [X] wks | 6.3 |
| 7.2 | Compliance evidence package | Closeout | Compliance | [X] wks | 7.1 |
| 7.3 | Retrospective & template archive | Closeout | PM | [X] wks | 7.2 |

# 6. RACI Matrix — Template

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Activity | Exec Spon. | CISO | PM | App Owner | Infra/DBA | Compl. |
| --- | --- | --- | --- | --- | --- | --- |
| Charter approval | A | C | R | I | I | I |
| Cryptographic inventory | I | A | C | R | R | I |
| Architecture & key mgmt design | I | A | C | C | R | C |
| Development / configuration | I | C | I | C | R | I |
| Testing & UAT | I | C | R | A | R | I |
| Production deployment approval | A | C | R | C | R | I |
| Legacy key destruction | I | A | I | I | R | C |
| Compliance evidence & sign-off | I | C | I | I | I | A/R |

# 7. Risk Register — Template

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Undiscovered system still using DES/3DES post-migration | Med | High | Multi-pass discovery incl. network traffic analysis; re-scan before closeout | Security Architecture |
| R-02 | Legacy hardware cannot support AES, requiring unplanned capital spend | Med | High | Early compatibility assessment (Phase 2); contingency budget line | Infrastructure |
| R-03 | Performance regression on high-throughput systems | Low | Med | Pre-production load testing; leverage AES-NI hardware acceleration | Performance Engineering |
| R-04 | Data loss/corruption during re-encryption of data at rest | Low | High | Backup before re-encryption; staged batch approach with checksums | DBAs |
| R-05 | Third-party/vendor system cannot be remediated on timeline | Med | Med | Early vendor engagement; contractual remediation clauses; compensating controls | Vendor Management |
| R-06 | Key management gaps (weak generation, poor rotation) | Low | High | Independent review of Key Management Plan against NIST SP 800-57 | CISO |
| R-07 | Compliance deadline missed | Low | High | Schedule buffer; phased rollout prioritizing regulated data first | PMO |

# 8. Key Management Plan — Template

This sub-plan should be developed in detail during Phase 3 (Design) and aligned to NIST SP 800-57 (Recommendation for Key Management).

| Lifecycle Stage | Requirement |
| --- | --- |
| Generation | Keys generated using an approved random bit generator; AES-128 minimum, AES-256 for high-sensitivity data, via a FIPS 140-3 validated module or HSM. |
| Distribution | Keys distributed via secure key-exchange mechanisms; no keys transmitted in plaintext or embedded in source code/config files. |
| Storage | Keys stored in an HSM or KMS with access restricted by role; no keys stored alongside the data they protect. |
| Rotation | Defined rotation schedule (e.g., annually or per data-sensitivity policy); automated rotation preferred over manual. |
| Legacy Key Handling | 3DES/DES keys retained only as long as needed to decrypt legacy data during the transition window, under restricted access. |
| Destruction | Cryptographic erasure or physical destruction of retired keys, logged and attested for audit purposes. |
| Audit & Monitoring | All key access and lifecycle events logged to a centralized, tamper-evident log; reviewed periodically by Security. |

# A. Appendix A — Industry Standards & Reference Framework

| Standard / Framework | Publisher | Relevance |
| --- | --- | --- |
| FIPS 197 | NIST | Advanced Encryption Standard specification (128/192/256-bit keys) — migration target. |
| SP 800-131A Rev. 2 (and draft Rev. 3) | NIST | Transition guidance for cryptographic algorithms and key lengths; source of the 3DES disallowance after Dec 31, 2023, and the pending 128-bit minimum by 2030. |
| SP 800-38 Series (A–F) | NIST | Recommended modes of operation for block ciphers (e.g., GCM, CBC, CTR); use to select the correct AES mode and avoid weak modes like ECB. |
| SP 800-57 (Parts 1–3) | NIST | Key management recommendations — basis for Section 8's Key Management Plan. |
| FIPS 140-3 | NIST | Security requirements for cryptographic modules; validated HSMs/KMS should hold current FIPS 140-3 validation. |
| PCI DSS v4.0 | PCI Security Standards Council | Payment card data protection requirements; explicitly disallows DES/3DES for cardholder data. |
| HIPAA Security Rule (45 CFR §164.312) | HHS | Addressable encryption safeguard for electronic protected health information. |
| NIST Cybersecurity Framework (CSF) 2.0 | NIST | Overarching risk-management context; maps this project to the PROTECT (Data Security) function. |
| ISO/IEC 27001:2022, Annex A.8.24 | ISO/IEC | Requires a documented cryptography policy and key management controls. |
| PMBOK Guide | PMI | Underlying project management framework for the phase structure, WBS, and RACI used in this document. |

Note: Standards and their revisions change over time (e.g., SP 800-131A Rev. 3 was in public draft as of late 2024). Before executing a migration from this template, confirm the current published version of each standard and the organization's applicable compliance deadlines.

# B. Appendix B — Glossary

| Term | Definition |
| --- | --- |
| AES | Advanced Encryption Standard — symmetric block cipher standardized in FIPS 197. |
| 3DES / TDEA | Triple Data Encryption Algorithm — legacy symmetric cipher applying DES three times; now disallowed for new encryption use. |
| HSM | Hardware Security Module — dedicated hardware for secure key generation, storage, and cryptographic operations. |
| KMS | Key Management System — software/service managing the cryptographic key lifecycle. |
| Mode of Operation | The algorithm defining how a block cipher processes data longer than one block (e.g., CBC, GCM, ECB). |
| Deprecated (NIST usage) | May be used but requires acceptance of a documented, specific risk. |
| Disallowed (NIST usage) | The algorithm/key length is no longer considered suitable for the stated use. |
| Legacy Use | Permitted only to process/decrypt previously protected information, not to newly protect data. |

# C. Appendix C — How to Reuse This Template

This document is designed to be genericized and reapplied to future migrations. To adapt it:

- Replace all bracketed placeholders (organization name, system names, dates, owners) with engagement-specific values.

- Re-validate Appendix A against the currently published version of each referenced standard — NIST transition guidance in particular is revised periodically.

- Adjust the Functional/Non-Functional Requirements (Sections 3.4–3.5) to the specific algorithm pair being migrated (e.g., SHA-1 → SHA-2/3, RSA → post-quantum).

- Retain the seven-phase SDLC structure, WBS, RACI, and Risk Register shells — these are algorithm-agnostic and reusable as-is.

- Archive the completed, populated document as a case study to accelerate the next migration cycle.